## December
Extraction Tool Release Task Sheet
December
Line # | Tasks | Subtask | Assigned | DD-Date | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | T
1 | Documentation | Review | Sam | 13-12-2019 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7
2 |  | Outline | Sam | 13-12-2019
3
4
5 | Bat start file | Bat file to open virtualtenv complete | David
6 |  | Executbale - start BAT, start ET | David
7
8 | [5 empty] | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14
9 | [14 empty] | Review of current documentation from original ET (Six Red Marbles)
10 | Licensing | Research module dependancies | David
11 |  | Review license options | David
12 |  | Assign license and update GitHub | David
13 |  | Update version for release | David
14
15 | VM Acquisition | Inquire | Sam | 16-12-2019 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21
16 | [6 empty] | Email Mike, find info on vendor VM setup. David and I require access to VM to install anaconda, python, and any other requirements to run ET. -------------------- Start outline of ET documentation/process | [7 empty] | Licensing for ET app |  | Licensing for ET app
17
18
19
20 | Set up VM | Python/Anaconda | David/Sam
21 |  | Virtual Environment | David/Sam
22 |  | Bat file | David |  |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28
23 |  | Executbale - start BAT, start ET | David |  | Batch Script/Executable: Test auto-start batch script and executable |  | Batch Script/Executable: Test auto-start batch script and executable | [5 empty] | Batch Script/Executable: Test auto-start batch script and executable |  | Batch Script/Executable & License: Due 12/27/2019
24
25
[6 empty] | 29 |  | 30 |  | 31 | Jan | 1
ALL DOCS & SETUP REQUIRED!!!

## master
Month
Item | Tasks | Subtask | Assigned | DD-Date | Sun |  | Mon |  | Tue |  | Wed |  | Thu |  | Fri |  | Sat |  | T
1 | [5 empty] | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7
2
3
4
5
6
7
8
9
10
11
12
13
14
15