## Sheet1
Alpha Testing Debug and Bug Fix Notes
To Do For Release (not bugs)
1. Release tag current alpha release
- Review version docs (pep 440)
- Tag Extraction Tool (dextract_application) with appropriate version
- Keep extract_base_code current with updates/fixes in extract_application
2. License App
- Check license of current third-party packages
- Create license for Extraction Tool App
3. Create executable for Beta release
1. Release tag current alpha release [ ] - Review version docs (pep 440) [ ] - Tag Extraction Tool (extract_application) with appropriate version [ ] - Keep extract_base_code current with updates/fixes in extract_application 2. License App [ ] - Check license of current third-party packages [ ] - Create license for Extraction Tool App 3. Create executable for Beta release
Extraction Tool Testing and Debugging
# | Bug Description | Status | File Name | Test Date (Tester) | Fix Date (Dev) | App Version | Comments/Notes
1 | Having no vocab words slide breaks app | Complete | 8309-02-15.pptx | 8/12/2019 (SW) | 8/20/2019 (drm) | v0.1-alpha | Error message
2 | Phrase for vocab word -- only first word shows | Complete | 8518-06-06.pptx | 8/12/2019 (SW) | 8/20/2019 (drm) | v0.1-alpha
3 | Vocab tab sometimes has capitalized first letter in file name | Complete | 8518-06-06.pptx | 8/12/2019 (SW) | 8/20/2019 (drm) | v0.2-alpha
4 | Extraction sheet is missing values for columns Frame, Slide Title, Type, Slide Layout, Filename, and Actual Est Time. PPT slide 8 extraction sheet line 15) | Complete | 8705-07-04.pptx | 8/13/2019 (SW) | 8/17/2019 (drm) | v0.2-alpha | Unable to reproduce 8507-07-04_xlsx
5 | Fails during extraction |  | 3112-09-02.ppt | 8/13/2019 (SW) |  | v0.2-alpha | Error message
6 | Extraction sheet is missing values for columns Frame, Slide Title, Type, Slide Layout, Filename, and Actual Est Time. PPT slide 17 (extraction sheet line 21) ------------------------------------------------------------------------------------------ PPT slide 21 (extraction sheet line 25): same as above | In Process | 8525-01-01.pptx | 8/13/2019 (SW) |  | v0.2-alpha | This is a PowerPoint formatting issue that has to be investigated, but it is not an application bug. Need to determine way to deliver an error msg for this.
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Note on H18: dmilatz: Windows User: (extract_env_1) PS C:\extract_application> python extract_build Exception in Tkinter callback Traceback (most recent call last): File "c:\users\sam.whindleton\appdata\local\continuum\anaconda3\Lib\tkinter\__init__.py", line 1705, in __call__ return self.func(*args) File "extract_build\extraction_pptx.py", line 181, in get_file read_slide(filename_path) File "extract_build\extraction_pptx.py", line 764, in read_slide vo_data_summary, f_name, voc_dict, UnboundLocalError: local variable 'voc_dict' referenced before assignment
Note on H22: dmilatz: Windows User: Exception in Tkinter callback Traceback (most recent call last): File "c:\users\sam.whindleton\appdata\local\continuum\anaconda3\Lib\tkinter\__init__.py", line 1705, in __call__ return self.func(*args) File "extract_build\extraction_pptx.py", line 181, in get_file read_slide(filename_path) File "extract_build\extraction_pptx.py", line 288, in read_slide for line in slide.notes_slide.notes_text_frame.text.split("\n"): AttributeError: 'NoneType' object has no attribute 'text'